## Data_Forms
Project Name
Jira ID
Github Repo | Vizzuality/project-name
EVM Inputs & Calculations
Project name: | Sample Project
Budget (PV total): |  | (Planned Value)
Cost to date (AC): |  | (Actual Cost)
% Completed (EV ratio 0..1): |  | (Estimation of Completed Value)
% Planned to date (0..1): |  | (Planned Value to date)
EV = | 0 | (Earned Value)
CPI (EV/AC) = | #N/A | (Cost Performance Index)
SPI (EV/PV proxy) = | #N/A | (Schedule Performance Index)
Notes
• Use % Planned as a proxy, for deliverables and milestones
• % values should be decimals: 70% → 0.70.
• These outputs feed the 'Data' sheet row 2 automatically (SPI, CPI, Overrun%).
On-Time Milestones (weighted) — Inputs & Calculations
OnTimeMilestones_0to1 = | 0.75 | (Result between 0 and 1)
Milestone | PlannedDate | ActualDate | CriticalityWeight | DueFlag | OnTimeFlag | WeightUsed | WeightedOnTime
Deliverable X | 2025-08-26 | 2025-08-19 | 1 | 1 | 1 | 1 | 1
Deliverable X | 2025-08-21 | 2025-08-20 | 1 | 1 | 1 | 1 | 1
Deliverable X | 2025-08-25 | 2025-08-19 | 1 | 1 | 1 | 1 | 1
Deliverable X | 2025-08-12 |  | 1 | 1 | 0 | 1 | 0
Deliverable X | 2026-01-15 |  | 1 | 0 |  | 0 | 0
Deliverable X | 2026-01-15 |  | 1 | 0 |  | 0 | 0
Deliverable X | 2026-01-15 |  | 1 | 0 |  | 0 | 0
Deliverable X | 2026-01-15 |  | 1 | 0 |  | 0 | 0
Deliverable X | 2026-01-15 |  | 1 | 0 |  | 0 | 0
Deliverable X | 2026-01-15 |  | 1 | 0 |  | 0 | 0
Deliverable X | 2026-01-15 |  | 1 | 0 |  | 0 | 0
Deliverable X | 2026-01-15 |  | 1 | 0 |  | 0 | 0
Notes
• Only milestones that are due (ActualDate filled OR today > PlannedDate + GraceDays) are counted in the denominator. • Late and still-open milestones (ActualDate blank and overdue) count as 0 in OnTimeFlag. • Use CriticalityWeight to give more weight to key milestones (e.g., 2 or 3). • Important: Don't add or remove lines!
Defect Density
# Bugs closed | 6 | *
# Tasks completed | 96 | Tasks are maximum of 100
DefectDensity_per_100Tasks | 6.25
Notes
• Update these values by clicking on the menu: Jira Metrics > Update Defect Density * The formula is (Bugs/Tasks)*100 * The target must be 3 or lower
Escaped Defects
EscapedRate_per_100Tasks (project total) | 0 | *
# Escaped defects (Staging + Production) | 0
Notes
• Number of bugs escaped to staing/production per 100 tasks • Update these values by clicking on the menu: Jira Metrics > Update Escaped Defects
MTTR
MTTR_hours | 0
# Incidents (MTTR scope) | 0
Notes
• Update these values by clicking on the menu: Jira Metrics > Update MTTR
Governance Compliance
Number of exceptions from the latest project peer review
Notes
• Fill The number of unjustified exceptions from the latest project peer review
Estimation for client satisfaction
Has the client complained about delays or delivery quality? | -
Has the client expressed dissatisfaction with design/implementation that remained unresolved? | -
What’s your overall estimation of client satisfaction 1 to 5?
Notes
• Fill with your own criteria
Automated test maturity
End2End tests
Unit Tests
Accesibility tests
Security tests
Front end tests
Notes
• Rate from 0 to 5 the lines above, where 0 is no tests, 3 is partial tests, and 5 is a good testing coverage
Lead time
Lead Time (days) | 32.0141 | Update from ready to develop | Review gmw
Notes
• Update from Jira Metrics > update lead time Lead Time measures the total elapsed time from when an issue enters the workflow (first “start” status such as New, Ready, or To Do) until it reaches a final “end” status (e.g., Done or Declined). It includes all time, both active work and waiting. A lower value indicates faster overall delivery.
Flow efficiency
Flow Efficiency 0 to 1 | 0.30758
Notes
• Update from Jira Metrics > update flow efficiency (Active time from to-do to done). Closer to 1 is better Flow Efficiency measures the ratio of active working time to the total lead time for each issue. Active time is accumulated only while the issue is in designated “active” statuses (e.g., In Progress, WIP, Code Review, QC). Flow Efficiency = Active Time / Total Time. A higher value indicates a more efficient workflow with less waiting or idle time.
Commitment Reliability
| Ratio | Committed(≥1 sprint) | Single-sprint | Multi-sprint
Commitment Reliability | 0.32424 | 330 | 107 | 223 | 0
Notes
• Update from Jira Metrics > update commitment reliability. Ratio of issues completed within the same sprint they were originally committed to. Closer to 1 indicates higher delivery consistency and planning accuracy.
PRs without review
PRs without review
Total merged
Notes
• Update from update Metrics > update PR review. Closer to 0 is better
PR review ratio
PR review ratio
Total merged
Notes
• This updates also with update Metrics > update PR review, no need to update again
Number of high-severity vulnerabilities remaining open for more than 30 days
High severity vulnerabilities |  | Error fetching dependabot | Check Amazonia 360
Notes
• Update from update Metrics > update PR review. Closer to 0 is better
Architecture checklist
Architecture documentation is up to date | 0 | The overall structure of the system — its components, data flow, and key technologies — is clearly defined and reflects the current implementation.
Infrastructure as Code implemented | 0 | All infrastructure (environments, services, pipelines, networks) is reproducible through code, ensuring consistency and version control.
Architecture Decision Records maintained | 0 | Important technical decisions and their rationale are recorded, enabling future teams to understand why certain approaches or technologies were chosen.
System / dependency diagrams are updated | 0 | The relationships between services, modules, and external systems are documented in a diagram that accurately represents how the system currently operates.
Notes
• Choose score 0 to 1
Ratio of user stories with no assigned reviewer
Total user stories | 15
User stories with one reviewer at least | 14
Notes
• Update from update Metrics > update QA metrics
End of project indicators
Strategic Impact
Select strategic impact | Medium impact: Supports one team or process improvement
Notes
• Strategic impact score (0–100) assessing how much the project contributes to company priorities. Represents business value and long-term relevance. Higher scores indicate stronger alignment with organizational goals or innovation outcomes. Entered manually at project closure by the Project Manager or Owner.
Client satisfaction survey
Understanding your needs
Proactivity
Communication
Overall time of delivery
Response time
Quality of deliverables
Met expectations
Likely to recommend
Notes
• Assign values 1 to 5 per the client satisfaction survey
Formulas:
DueFlag = IF(OR([ActualDate]<>"",TODAY()>[PlannedDate]+GraceDays),1,0)
OnTimeFlag = IF([ActualDate]<>"",IF([ActualDate]<=[PlannedDate]+GraceDays,1,0),IF(TODAY()>[PlannedDate]+GraceDays,0,""))

## Params
Targets
Name (use as Named Range) | Value | Unit/Type | Notes
DefDensity_t | 3 | defects/100 tasks | Target max defect density. Used in P_quality (sub-indicator defect density). ≤ target scores 100%.
Escaped_t | 0.01 | escapes/100 tasks | Target max escaped defects. Used in P_quality (sub-indicator escaped rate). ≤ target scores 100%.
MTTR_t | 24 | hours | Target mean time to recover (hours). Used in P_quality (sub-indicator MTTR). ≤ target scores 100%.
SPI_t | 1 | ratio | Target schedule performance index. Used in P_time (sub-indicator SPI). Optional, default 1 = on track.
CPI_t | 1 | ratio | Target cost performance index. Used in P_cost (sub-indicator CPI). Optional, default 1 = on budget.
LT_t | 3 | max days | Target maximum lead time. Used in P_flow (sub-indicator Lead Time)
FE_t | 0.4 | ratio | Target ratio flow efficiency
WIP_max | 4 | count | Max recommended Work In Progress items. Used in P_flow (sub-indicator WIP breaches). TBI.
CFR_max | 0.15 | ratio | Deprecated. Previously used in Change Failure Rate.
ROI_t | 1 | ratio | ROI target. Used in P_value (sub-indicator ROI).
IaC_t | 0.9 | ratio | Target coverage for Infrastructure as Code. Used in P_engineering (sub-indicator IaC coverage).
HighVuln_t | 0 | count | Target max high-severity vulnerabilities open >30 days (0 = strict compliance)
CritRisk_t | 0 | count | Target max overdue critical risks at closure (0 = none tolerated)
GovExc_t | 2 | count | Max tolerated exceptions. If < 2 score will always be 0 when there are excceptions
PR_noReview_t | 0.02 | ratio | Target percentage of pull requests with no reviewer (min. 1 to 50)
Quality Weights
Name (use as Named Range) | Value | Unit/Type | Notes
W_def | 0.05 | weight | Defect density in P_quality
W_esc | 0.2 | weight | Escaped rate in P_quality
W_mttr | 0.05 | weight | MTTR in P_quality (Mean Time To Resolution)
W_q_storyrev | 0.3 | weight | Stories without a reviewer in P_qauality
W_qual_gov | 0.3 | weight | governance compliance in P_quality
W_q_pr | 0.1 | weight | Pull request review ratio in P_quality
W_q_design | 0 | weight | Design quality in P_quality
W_q_science | 0 | weight | Data science in P_quality
| 1 | validator
Time Weights
Name (use as Named Range) | Value | Unit/Type | Notes
W_time_spi | 0.6 | weight | SPI in P_time calculation
W_time_milestones | 0.4 | weight | for OnTimeMilestones in P_time
| 1 | validator
Cost Weights
Name (use as Named Range) | Value | Unit/Type | Notes
W_cost_cpi | 0.7 | weight | CPI (cost efficiency) in P_cost
W_cost_var | 0.3 | weight | Budget Variance (overrun %) in P_cost
| 1 | validator
Value Weights
Name (use as Named Range) | Value | Unit/Type | Notes
W_value_roi | 0.7 | weight | ROI inside p_value
W_value_okr | 0.3 | weight | OKR inside p_value
| 1 | validator
Satisfaction Weights
Name (use as Named Range) | Value | Unit/Type | Notes
W_sat_client | 0.8 | weight | final client satisfaction in P_satisfaction
W_sat_pm | 0.2 | weight | PM estimation of client satisfaction in P_satisfaction
| 1 | validator
W_cs_understanding | 0.12 |  | Client survey weight
W_cs_proactivity | 0.12 |  | Client survey weight
W_cs_communication | 0.1 |  | Client survey weight
W_cs_time | 0.14 |  | Client survey weight
W_cs_response | 0.1 |  | Client survey weight
W_cs_quality | 0.24 |  | Client survey weight
W_cs_expect | 0.12 |  | Client survey weight
W_cs_recommend | 0.06 |  | Client survey weight
| 1 | validator
Efficiency Weights
Name (use as Named Range) | Value | Unit/Type | Notes
W_flow_lt | 0.4 | weight | time in P_efficiency
W_flow_fe | 0.3 | weight | for flow efficiencye in P_efficiency
W_flow_cr | 0.3 | weight | for commitment reliability in P_efficiency
| 1 | validator
Engineering Weights
Name (use as Named Range) | Value | Unit/Type | Notes
W_eng_test | 0.5 | weight | test maturity in P_engineering
W_eng_pr | 0.2 | weight | PR review ratio in P_engineering
W_eng_iac | 0 | weight | IaC coverage in P_engineering (Infrastructure as Code)
W_eng_arch | 0.3 | weight | architecture checklist in P_engineering
| 1 | validator
Risk Weights
Name (use as Named Range) | Value | Unit/Type | Notes
W_risk_pr | 0.5 | weight | PR with no reviewer P_risk
W_risk_vuln | 0.5 | weight | HighVuln_open_gt30d in P_risk
W_risk_risks | 0 | weight | RisksCriticalOverdue in P_risk
1
Global Weights
Name (use as Named Range) | Value | Unit/Type | Notes
W_time | 0.12 | weight | P_time
W_cost | 0.1 | weight | P_costs
W_quality | 0.18 | weight | P_quality
W_value | 0.1 | weight | P_value
W_risk | 0.05 | weight | P_risk
W_flow | 0.15 | weight | P_flow
W_engineering | 0.18 | weight | P_engineering
W_satisfaction | 0.12 | weight | P_satisfaction
| 1 | validator
Gates & Constants
Name (use as Named Range) | Value | Unit/Type | Notes
Sev1_cap | 60 | points | max P_quality if Sev1
GraceDays | 3 | days | schedule grace window
Bonus_max | 0.1 | points | optional bonus cap (Top 5 projects)
Test Maturity Weights
Name (use as Named Range) | Value | Unit/Type | Notes
W_test_e2e | 0.4 | weight
W_test_unit | 0.1 | weight
W_test_access | 0.1 | weight
W_test_security | 0.2 | weight
W_test_frontend | 0.2 | weight
| 1 | validator

## Data
SPI | OnTimeMilestones_0to1 | CPI | BudgetVariance_OverrunPct | PM_ClientSatisfaction_0to1 | DefectDensity_per_100Tasks | GovernanceCompliance_score_0to100 | EscapedRate_per_100Tasks | MTTR_hours | TestMaturity_percent | LeadTime_days | FlowEfficiency_0to1 | CommitmentReliability_0to1 | PRsWithoutReview_count | HighVuln_open_gt30d | PR_review_ratio_0to1 | ArchChecklist_0to4 | StoriesWithoutReviewer_ratio_0to1 | OKR_Impact_0to100 | ClientSatisfaction
#N/A | 0.75 | #N/A | 0 | 0.65 | 6.25 | 1 | 0 | 0 | 0.5 | 32.0141 | 0.30758 | 0.32424 |  |  |  | 0 | 0.93333 | 0.5
Schedule Performance Index | Percentage of milestones delivered on time | Cost Performance Index | Percentage by which Actual Cost exceeds Budget (0 if within budget) | Composite client satisfaction score (0–1) based on delivery complaints, design complaints, and PM overall estimation. | Number of defects found per 100 tasks delivered | Score (0–100) based on project peer review exceptions, with a threshold in GovEx_t. | Bugs escaped to production per 100 tasks | Average number of hours it takes to resolve a critical incident, measured from the moment it’s created until it’s marked as resolved. | Percentage of key testing categories implemented (unit, e2e, usability, security, frontend). | Average elapsed time in days from “To Do” to “Done”. | Ratio of active work time in progress vs. total time from “To Do” to “Done” (0–1). | Ratio of issues completed versus issues committed at sprint start (0–1). | Number of pull request without review | Number of high-severity vulnerabilities remaining open for more than 30 days. | Ratio of merged PRs that received at least one review (0–1). | Architecture checklist score from 0 to 4. | Ratio of user stories with no assigned reviewer (≥1 required). | Impact score (0–100) based on contribution to strategic objectives (OKRs). | Overall client satisfaction score, typically from end-of-project survey or PM assessment.
EV / PV | # milestones on time / total milestones | EV / AC | (AC - Budget) / Budget * 100 | Survey/PM score on 0-100 scale | (Closed bugs / Completed tasks) * 100 | MAX(0, 1 − (#exceptions / threshold)) | (Escaped bugs / Completed tasks) * 100 | Average(hours between incident created and resolved) | (# testing categories implemented / total categories) * 100 | Average(Done_date − ToDo_date) in days | Active work time / Total elapsed time | Completed committed issues / Total committed issues | Count(Github pull request reviewer: *) | Count(GitHub Dependabot alerts severity≥High AND age>30d) | Merged PRs with ≥1 review / Total merged PRs | Sum of checklist items met (0–4) | Count(Stories with Reviewer_count=0) / Count(Stories total) | Manual score 0–100 from OKR contribution | End-of-project survey score (or PM proxy if missing)
P_time | P_time | P_cost | P_cost | P_satisfaction | P_quality | P_quality | P_quality | P_quality | P_engineering | P_flow | P_flow | P_flow | P_risk | P_risk | P_engineering | P_engineering | P_quality | P_value | P_satisfaction
[18 empty] | End of project indicator | End of project indicator

## Scores
P_time | P_cost | P_quality | P_value | P_satisfaction | P_flow | P_engineering | P_risk
#N/A | #N/A | 90 | 1 | 65 | 37 | 35 | 50
Schedule adherence score (0–100) combining SPI and on-time milestone delivery. SPI is normalized to the target (SPI_t) and capped at 1; milestone punctuality is a 0–1 ratio. Weights are controlled by W_time_spi and W_time_milestones. Neutral handling: if an input is blank, a neutral 0.5 is used so in-progress projects aren’t penalized. | Budget adherence score (0–100) combining cost efficiency (CPI) and budget overrun %. CPI is normalized to the target (CPI_t) and capped at 1. Overrun converts to a 0–1 score as 1 − overrun, floored at 0. Weights come from W_cost_cpi and W_cost_var. Blanks use a neutral 0.5 so in-progress projects aren’t penalized. | Overall result quality score (0–100). Combines defect density, governance compliance, escaped defect rate, MTTR, and (at project closure) design and science quality. Each metric is normalized to a 0–100 scale. If blank, contributes neutrally (50). If a Sev-1 production incident occurred (Sev1_in_prod_0or1=1), the score is capped at Sev1_cap. | Business/strategic value score (0–100). Based solely on OKR impact (OKR_Impact_0to100). The score reflects the achieved business or strategic impact at project completion. If the OKR impact is blank during execution, it contributes neutrally (0.5). | Client satisfaction score (0–100). At closure, combines client survey (80%) and PM CSAT (20%). During development, uses PM CSAT only. If both are missing, defaults to neutral (0.5). | Delivery flow score (0–100). Combines lead time, flow efficiency, and commitment reliability. Lead time is normalized to LT_t (target maximum days); flow efficiency to FE_t (target ratio); commitment reliability is direct (0–1). Weights controlled by W_flow_lt, W_flow_fe, and W_flow_cr. If any input is blank, it contributes neutrally (0.5). | Engineering discipline score (0–100). Combines test maturity, PR review ratio, IaC coverage, and architecture checklist. Each input is normalized to 0–100. If blank, contributes neutrally (50). Weights sum to 1. | Risk posture score (0–100). Combines two governance and technical risk indicators: • PRs merged without review (from GitHub) — proportion of pull requests merged without an approved review. • High-severity vulnerabilities >30 days (from GitHub Security) — unresolved critical vulnerabilities older than 30 days. Each metric is normalized on a 0–1 scale, where lower values indicate lower risk. If data is missing, a neutral fallback of 0.5 is used.
Total Score | #N/A